#### UNICEF Toolkit on Diversion and Alternatives to Detention 2009

Sample evaluation methodology plan for an annual review

| Indicator # | What info is needed? | Source of info? | How to collect info | Resources needed | Who will collect info? | When? | Risk factors / obstacles | Steps to overcome obstacles |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1. 20% reduction in number of children in pre-trial detention within a 12-month period in Sample Region after 1 year [baseline = 121 boys & 5 girls] | Essential: Number of children (boys and girls) under 18 in pre-trial detention for 12-month period in Sample Region. Desirable: ages and alleged offences for each case. | Monthly police and remand centre records – held on file at Central Police HQ & 2 remand homes individually | Compile monthly data from police and remand centre records | Transport to Central Police HQ & 2 remand homes; Same Excel spreadsheet format used for baseline data collection | Police representative from Steering Committee will provide raw data to external evaluator for compilation | Days 1-3 of evaluation | If forms have not been filled in correctly, there may be double-counting of the same children each month rather than new arrests / referrals. | Ongoing monitoring should have mitigated this risk, but spot check of children’s names may be necessary. |
| 2. 60% of children benefiting from diversion programmes in Sample Region show ‘significant improvement’ in terms of behaviour on completion of programme. | Essential: Total number of children (boys and girls) who have completed diversion programmes in Sample Region in past 12 months. Desirable: ages and alleged offences for each case. | Monthly records for each of the 2 diversion projects in Sample Region | Compile monthly data from diversion projects | External evaluator transport to 2 diversion projects to review / compiled data on-site | 2 Project Coordinators will provide raw data to external evaluator for compilation | Days 1-2 of evaluation | Project Coordinators may not have info ready in time for external evaluator | Contact 2 Project Coordinators 1month in advance setting out full list of data required for the evaluation & when, explaining importance of evaluation & how data will be used |
|  | Essential: Documentation of behaviour of each child who has completed the diversion programme on entry and exit of the diversion programme | Completed project ‘entry’ and ‘exit‘ ‘behaviour assessment forms’ completed by child, project worker and parent for each child who has completed diversion programme in the past 12 months from the 2 diversion projects in Sample Region | Compile ‘entry’ and ‘exit’ forms from diversion projects [‘significant improvement’ is measured as a jump of 3 points in at least 3 behaviour areas by at least 2 sources (child, parent or project worker)] |  | 2 Project Coordinators will provide raw data to external evaluator for compilation | Days 3-5 of evaluation | Gaps in forms – e.g. not all behaviour categories completed for both ‘entry’ and ‘exit’ or not a full set of child / parent / project worker forms for each child or some case forms missing | Request 2 Project Coordinators in advance to check for gaps, to follow up and complete gaps where possible, and/or to justify gaps which cannot be filled; external evaluator to take into consideration completed data only for official statistics, and note results for incomplete data separately |
|  | Desirable: Qualitative feedback from children, parents and social workers on how the diversion programme has impacted on behaviour | Selection of children & their parents who have completed diversion programmes; project workers from 2 diversion projects | Focus group discussions and/or individual interviews | Consent forms for children and parents; Venue; Refreshments; Transport for participants Flipcharts & pens Materials to note case studies | External evaluator | Days 3-5 of evaluation | Children who have completed programme (and their parents) may not want to be involved; possible self-selection of participants may result in biased positive feedback | Prepare and disseminate a simple but attractive leaflet / letter explaining the importance of the evaluation and potential benefits for other children / opportunity for beneficiaries and parents to have their say |
| Etc. |  |  |  |  |  |  |  |  |